## Activity Description
Activity ID | Activity | Predecessors | Duration
A_1 | 1.1.1 Initial Site Review |  | 1
A_2 | 1.1.2.1 Determine Project Roles | A_1 | 1
A_3 | 1.1.2.2 Brainstorm Project Ideas | A_1 | 1
A_4 | 1.1.2.3 Determine Final Scope of Project | A_3 | 1
A_5 | 1.1.2 Create Charter | A_2, A_4 | 1
A_6 | 1.1.3 Final Site Review with Materials | A_16, A_17 | 1
A_7 | 1.2.1 Sketch Proposed RGM | A_5, A_13 | 2
A_8 | 1.2.2.1 Determine Project Components | A_7 | 1
A_9 | 1.2.2.2 Determine Cost and Time to Each Component | A_8 | 1
A_10 | 1.2.2.3 Assign Member to Each Component | A_8 | 1
A_11 | 1.2.2.4 Determine Risk Factors for Each Component | A_9, A_10 | 1
A_12 | 1.2.2 Generate WBS | A_11 | 1
A_13 | 1.2.3 Measure Area and Assign Co-ords | A_1 | 1
A_15 | 1.3.1 Discuss Required Materials | A_12 | 3
A_16 | 1.3.2 Dollarama Spree | A_15 | 1
A_17 | 1.3.3 Collect Materials from Home | A_15 | 3
A_18 | 1.3.4 Report Earned Value Analysis | A_16, A_17 | 2
A_19 | 1.4.1 Gantt Diagram Development | A_6, A_18 | 2
A_20 | 1.4.2 Network Activity Diagram | A_19 | 1
A_22 | 1.5.1.1 Build Team Member 1 Section | A_20 | 4
A_23 | 1.5.1.2 Test and Adjust Section 1 Off-Site | A_22 | 2
A_24 | 1.5.1 Finalize Section 1 Build and Communicate Design Changes | A_23 | 2
A_25 | 1.5.2.1 Build Team Member 2 Section | A_20 | 4
A_26 | 1.5.2.2 Test and Adjust Section 2 Off-Site | A_25 | 2
A_27 | 1.5.2 Finalize Section 2 Build and Communicate Design Changes | A_26 | 2
A_28 | 1.5.3.1 Build Team Member 3 Section | A_20 | 4
A_29 | 1.5.3.2 Test and Adjust Section 3 Off-Site | A_28 | 2
A_30 | 1.5.3 Finalize Section 3 Build and Communicate Design Changes | A_29 | 2
A_31 | 1.5.4.1 Build Team Member 4 Section | A_20 | 4
A_32 | 1.5.4.2 Test and Adjust Section 4 Off-Site | A_31 | 2
A_33 | 1.5.4 Finalize Section 4 Build and Design Changes | A_32 | 2
A_34 | 1.5.5.1 Build Team Member 5 Section | A_20 | 4
A_35 | 1.5.5.2 Test and Adjust Section 5 Off-Site | A_34 | 2
A_36 | 1.5.5 Finalize Section 4 Build and Design Changes | A_35 | 2
A_37 | 1.6.1 Move and Combine All Sections On-Site | A_24, A_27, A_30,A_33,A_36 | 3
A_38 | 1.6.2 Test and Adjust Section 1 | A_37 | 3
A_39 | 1.6.3 Test and Adjust Section 2 | A_37 | 3
A_40 | 1.6.4 Test and Adjust Section 3 | A_37 | 3
A_41 | 1.6.5 Test and Adjust Section 4 | A_37 | 3
A_42 | 1.6.6 Test and Adjust Section 5 | A_37 | 3
A_43 | 1.6.6 Test whole machine and make final adjustments | A_38, A_39,A_40,A_41,A_42 | 2
A_44 | 1.7.1 Operate and Take Video of RGB On-Site | A_43 | 1
A_45 | 1.7.2 Tear Down RGB | A_44 | 1
A_46 | 1.8.1 Submit RGB Video | A_45 | 1
A_47 | 1.8.2 Determine Final Earned Value Analysis | A_46 | 1
A_48 | 1.8.3 Final Meeting (Celebration) | A_47 | 1

## Network Activity Diagram
**** The corresponding activity description for each ID on the diagram can be found in the tab "Activity Description"
The Project End Date is Scheduled for April 1, 2020
| ES | ID | EF | [40 empty] | 21 | A_22 | 25 | 25 | A_23 | 27 | 27 | A_24 | 29
| Slack | [42 empty] | 0 |  |  | 0 |  |  | 0
| LS | DUR | LF | [40 empty] | 21 | 4 | 25 | 25 | 2 | 27 | 27 | 2 | 29
[56 empty] | 32 | A_38 | 35
0
[56 empty] | 32 | 3 | 35
|  |  |  | 1 | A_2 | 2 |  |  |  |  | 3 | A_5 | 4
|  |  |  | 1 | [6 empty] | 0 | [8 empty] | 7 | A_9 | 8
|  |  |  | 2 | 1 | 3 |  |  |  |  | 3 | 1 | 4 | [6 empty] | 0
[20 empty] | 7 | 1 | 8
[14 empty] | 4 | A_7 | 6 | [15 empty] | 13 | A_16 | 14 | 16 | A_6 | 17 | [6 empty] | 21 | A_25 | 25 | 25 | A_26 | 27 | 27 | A_27 | 29
| 0 | A_1 | 1 | [10 empty] | 0 | [8 empty] | 8 | A_11 | 9 | 9 | A_12 | 10 |  |  |  | 2 |  |  | 1 | [8 empty] | 0 |  |  | 0 |  |  | 0
| 0 | [12 empty] | 4 | 2 | 6 | [6 empty] | 0 |  |  | 0 | [5 empty] | 15 | 1 | 16 | 17 | 1 | 18 | [6 empty] | 21 | 4 | 25 | 25 | 2 | 27 | 27 | 2 | 29
| 0 | 1 | 1 | [13 empty] | 6 | A_8 | 7 |  |  |  | 8 | 1 | 9 | 9 | 1 | 10 | [27 empty] | 32 | A_39 | 35
[17 empty] | 0 | [38 empty] | 0
[17 empty] | 6 | 1 | 7 | [36 empty] | 32 | 3 | 35
[20 empty] | 7 | A_10 | 8
|  |  |  | 1 | A_3 | 2 |  | 2 | A_4 | 3 | [9 empty] | 0
|  |  |  | 0 |  |  |  | 0 | [11 empty] | 7 | 1 | 8
|  |  |  | 1 | 1 | 2 |  | 2 | 1 | 3 | [18 empty] | 10 | A_15 | 13
0
[29 empty] | 10 | 3 | 13
[32 empty] | 13 | A_17 | 16 | 16 | A_18 | 18 | 18 | A_19 | 20 | 20 | A_20 | 21
[5 empty] | 1 | A_13 | 2 | [24 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
[5 empty] | 2 | [26 empty] | 13 | 3 | 16 | 16 | 2 | 18 | 18 | 2 | 20 | 20 | 1 | 21
[5 empty] | 3 | 1 | 4 | [36 empty] | 21 | A_28 | 25 | 25 | A_29 | 27 | 27 | A_30 | 29 | 29 | A_37 | 32
[44 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
[44 empty] | 21 | 4 | 25 | 25 | 2 | 27 | 27 | 2 | 29 | 29 | 3 | 32
[56 empty] | 32 | A_40 | 35 | 35 | A_43 | 37 | 37 | A_44 | 38 | 38 | A_45 | 39 | 39 | A_46 | 40 | 40 | A_47 | 41 | 41 | A_48 | 42
[56 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[56 empty] | 32 | 3 | 35 | 35 | 2 | 37 | 37 | 1 | 38 | 38 | 1 | 39 | 39 | 1 | 40 | 40 | 1 | 41 | 41 | 1 | 42
[44 empty] | 21 | A_31 | 25 | 25 | A_32 | 27 | 27 | A_33 | 29
[44 empty] | 0 |  |  | 0 |  |  | 0
[44 empty] | 21 | 4 | 25 | 25 | 2 | 27 | 27 | 2 | 29
[56 empty] | 32 | A_41 | 35
0
[56 empty] | 32 | 3 | 35
[44 empty] | 21 | A_34 | 25 | 25 | A_35 | 27 | 27 | A_36 | 29
[44 empty] | 0 |  |  | 0 |  |  | 0
[44 empty] | 21 | 4 | 25 | 25 | 3 | 27 | 27 | 2 | 29
[56 empty] | 32 | A_42 | 35
0
[56 empty] | 32 | 3 | 35

## PERT & PROBABILITY
Activity ID | Predecessors | Expected | Pessimistic | Optimistic | PERT Calculation | St. dev | Variance | Critical Path | CP Variance | CP Expected
A_1 |  | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778 | 1.1667 | 0.027778 | 1 | EXPECTED TIME (Te) | 44.33
A_2 | A_1 | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778 |  |  |  | TOTAL PATH VARIANCE | 7.3889
A_3 | A_1 | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778 | 1.1667 | 0.027778 | 1 | TOTAL PATH ST. DEV | 2.7183
A_4 | A_3 | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778 | 1.1667 | 0.027778 | 1
A_5 | A_2, A_4 | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778 | 1.1667 | 0.027778 | 1 | SCHEDULED TIME (Te) | Duration | Z Score = (Ts-Te)/ total path St. Dev | Probability
A_6 | A_16, A_17 | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778
A_7 | A_5, A_13 | 2 | 3 | 1 | 2 | 0.33333 | 0.11111 | 2 | 0.11111 | 2 | Initial Scheduled Time | 42 | -0.85717 | 19.49%
A_8 | A_7 | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778 | 1.1667 | 0.027778 | 1 | 1 day late | 43 | -0.48929 | 31.32%
A_9 | A_8 | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778 | 1.1667 | 0.027778 | 1 | 2 days late | 44 | -0.1214 | 45.22%
A_10 | A_8 | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778 |  |  |  | 3 days late | 45 | 0.24648 | 59.87
A_11 | A_9, A_10 | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778 | 1.1667 | 0.027778 | 1 | 4 days late | 46 | 0.61437 | 72.91
A_12 | A_11 | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778 | 1.1667 | 0.027778 | 1
A_13 | A_1 | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778 |  |  |  | The probability that the project will be no more than 4 days late from its original due date is 72.91%
A_15 | A_12 | 3 | 4 | 2 | 3 | 0.33333 | 0.11111 | 3 | 0.11111 | 3
A_16 | A_15 | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778
A_17 | A_15 | 3 | 4 | 2 | 3 | 0.33333 | 0.11111 | 3 | 0.11111 | 3
A_18 | A_16, A_17 | 2 | 3 | 1 | 2 | 0.33333 | 0.11111 | 2 | 0.11111 | 2
A_19 | A_6, A_18 | 2 | 3 | 1 | 2 | 0.33333 | 0.11111 | 2 | 0.11111 | 2
A_20 | A_19 | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778 | 1.1667 | 0.027778 | 1
A_22 | A_20 | 4 | 5 | 3 | 4 | 0.33333 | 0.11111 | 4 | 0.11111 | 4
A_23 | A_22 | 2 | 3 | 1 | 2 | 0.33333 | 0.11111 | 2 | 0.11111 | 2
A_24 | A_23 | 2 | 3 | 1 | 2 | 0.33333 | 0.11111 | 2 | 0.11111 | 2
A_25 | A_20 | 4 | 5 | 3 | 4 | 0.33333 | 0.11111
A_26 | A_25 | 2 | 3 | 1 | 2 | 0.33333 | 0.11111
A_27 | A_26 | 2 | 3 | 1 | 2 | 0.33333 | 0.11111
A_28 | A_20 | 4 | 5 | 3 | 4 | 0.33333 | 0.11111
A_29 | A_28 | 2 | 3 | 1 | 2 | 0.33333 | 0.11111
A_30 | A_29 | 2 | 3 | 1 | 2 | 0.33333 | 0.11111
A_31 | A_20 | 4 | 5 | 3 | 4 | 0.33333 | 0.11111
A_32 | A_31 | 2 | 3 | 1 | 2 | 0.33333 | 0.11111
A_33 | A_32 | 2 | 3 | 1 | 2 | 0.33333 | 0.11111
A_34 | A_20 | 4 | 5 | 3 | 4 | 0.33333 | 0.11111
A_35 | A_34 | 2 | 3 | 1 | 2 | 0.33333 | 0.11111
A_36 | A_35 | 2 | 3 | 1 | 2 | 0.33333 | 0.11111
A_37 | A_24, A_27, A_30,A_33,A_36 | 3 | 4 | 2 | 3 | 0.33333 | 0.11111 | 3 | 3 | 3
A_38 | A_37 | 3 | 4 | 2 | 3 | 0.33333 | 0.11111 | 3 | 3 | 3
A_39 | A_37 | 3 | 4 | 2 | 3 | 0.33333 | 0.11111
A_40 | A_37 | 3 | 4 | 2 | 3 | 0.33333 | 0.11111
A_41 | A_37 | 3 | 4 | 2 | 3 | 0.33333 | 0.11111
A_42 | A_37 | 3 | 4 | 2 | 3 | 0.33333 | 0.11111
A_43 | A_38, A_39,A_40,A_41,A_42 | 2 | 3 | 1 | 2 | 0.33333 | 0.11111 | 2 | 0.11111 | 2
A_44 | A_43 | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778 | 1.1667 | 0.027778 | 1
A_45 | A_44 | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778 | 1.1667 | 0.027778 | 1
A_46 | A_45 | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778 | 1.1667 | 0.027778 | 1
A_47 | A_46 | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778 | 1.1667 | 0.027778 | 1
A_48 | A_47 | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778 | 1.1667 | 0.027778 | 1
[5 empty] | TOTALS | 12.1667 | 3.5278 | 44.3333 | 7.3889 | 42

## Level
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Gant Before
Enter Company Name in cell B2.
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  | Project Start: |  | 2020-01-29
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  |  | 2020-01-27 | [6 empty] | 2020-02-03 | [6 empty] | 2020-02-10 | [6 empty] | 2020-02-17 | [6 empty] | 2020-02-24 | [6 empty] | 2020-03-02 | [6 empty] | 2020-03-09 | [6 empty] | 2020-03-16 | [6 empty] | 2020-03-23 | [6 empty] | 2020-03-30 | [6 empty] | 2020-04-06 | [6 empty] | 2020-04-13
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2020-01-27 to 2020-04-19
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2020-01-27 to 2020-04-19
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | 1.1 Project Initiation and Planning
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | 1.1.1 Initial Site Review | Everyone | 100% | 2020-01-29 | 2020-02-01 | 4
1.1.2 | 1.1.2 Create Charter | Everyone | 100% | 2020-02-01 | 2020-02-03
| 1.1.2.1 determine project roles | Everyone | 100% | 2020-02-01 | 2020-02-01
| 1.1.2.2 brainstorm project ideas | Everyone | 100% | 2020-02-02 | 2020-02-02
| 1.1.2.3 Determine final scope | Everyone | 100% | 2020-02-03 | 2020-02-03
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | 1.1.3 Final Site review with materials | Everyone | 100% | 2020-02-01 | 2020-02-01 | 1
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | 1.2 RGM Layout Activities
| 1.2.1 Sketch the proposed RGM | Everyone | 100% | 2020-02-01 | 2020-02-02 | 2
| 1.2.2 Generate WBS | Everyone | 100% | 2020-02-02 | 2020-02-05 | 4
| 1.2.2.1 determine components of project | Everyone | 100% | 2020-02-02 | 2020-02-03
| 1.2.2.2 determine cost and time to each component | Everyone | 100% | 2020-02-02 | 2020-02-03
| 1.2.2.3 assign member to each component | Everyone | 100% | 2020-02-04 | 2020-02-04
| 1.2.2.4 determine risk factors for each component | Everyone | 100% | 2020-02-05 | 2020-02-05
| 1.2.3 Measure area and assign co-ords | Everyone | 100% | 2020-02-06 | 2020-02-07 | 2
| 1.2.4 Research risk's and limitations | Everyone | 100% | 2020-02-06 | 2020-02-08 | 3
Sample phase title block | 1.3 Purchase Items
| 1.3.1 Discuss required materials | Everyone | 100% | 2020-02-13 | 2020-02-18 | 6
| 1.3.2 Dollarama spree | Everyone | 100% | 2020-02-16 | 2020-02-21 | 6
| 1.3.3 collect materials from home | Everyone | 100% | 2020-02-19 | 2020-02-23 | 5
| 1.3.4 report earned value analysis | Everyone | 100% | 2020-03-05 | 2020-03-10
Sample phase title block | 1.4 Project Scheduling and Planning
| 1.4.1 Gannt Diagram Development | Everyone | 100% | 2020-02-11 | 2020-02-11 | 1
| 1.4.2 Network Activity Diagram | Everyone | 100% | 2020-02-13 | 2020-02-13 | 1
1.4.3 | 1.4.3 Monitor and Control Planning | Everyone | 100% | 2020-02-11 | 2020-03-15 | bar: 2020-02-12 to 2020-03-13
Sample phase title block | 1.5 Build RGM
| 1.5.1 Build Team Member 1 section | Hedaya | 100% | 2020-03-05 | 2020-03-25 | 21
| 1.5.2 Build Team Member 2 section | Kajal | 100% | 2020-03-05 | 2020-03-25 | 21
| 1.5.3 Build Team Member 3 section | Nada | 100% | 2020-03-05 | 2020-03-25 | 21
| 1.5.4 Build Team Member 4 section | Abigail | 100% | 2020-03-05 | 2020-03-25 | 21
| 1.5.5 Build Team Member 5 section | Nicholas | 100% | 2020-03-05 | 2020-03-25 | 21
Sample phase title block | 1.6 RGM Operate and Tear Down
| 1.6.1 RGM Operate | Everyone | 100% | 2020-03-25 | 2020-03-25 | 1
| 1.6.2 Tear Down | Everyone | 100% | 2020-04-02 | 2020-04-02 | 1
Sample phase title block | 1.7 Reflect on the Project
| 1.7.1 Video Submission | Everyone | 100% | 2020-04-01 | 2020-04-01 | 1
| 1.7.2 Determine final earned value analysis | Everyone | 100% | 0 | 0 | 1
| 1.7.3 Final meeting (celebration) | Everyone | 100% | 2020-04-01 | 2020-04-01 | 1
Gant After
| Persay we lose Hedaya and Kajal, This is the new proposed Gant Diagram | Project Start: |  | 2020-01-29
|  | Display Week: |  | 1 |  |  |  | 2020-01-27: 2020-01-27; 2020-02-03: 2020-02-03; 2020-02-10: 2020-02-10; 2020-02-17: 2020-02-17; 2020-02-24: 2020-02-24; 2020-03-02: 2020-03-02; 2020-03-09: 2020-03-09; 2020-03-16: 2020-03-16; 2020-03-23: 2020-03-23; 2020-03-30: 2020-03-30; 2020-04-06: 2020-04-06; 2020-04-13: 2020-04-13
Description | time axis 2020-01-27 to 2020-04-19
| TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | DAYS ADJ | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
| 1.1 Project Initiation and Planning | [90 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.1.1 Initial Site Review | Everyone | 0% | 2020-01-29 | 2020-02-04 | 4 | 7 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.1.2 Create Charter | Everyone | 0% | 2020-02-04 | 2020-02-08 | 3 | 5 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.1.2.1 determine project roles | Everyone | 0% | 2020-02-04 | 2020-02-05 | 1 | 2 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.1.2.2 brainstorm project ideas | Everyone | 0% | 2020-02-05 | 2020-02-06 | 1 | 2 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.1.2.3 Determine final scope | Everyone | 0% | 2020-02-06 | 2020-02-07 | 1 | 2 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.1.3 Final Site review with materials | Everyone | 0% | 2020-02-04 | 2020-02-05 | 1 | 2 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
1.2 RGM Layout Activities
| 1.2.1 Sketch the proposed RGM | Everyone | 0% | 2020-02-01 | 2020-02-04 | 2 | 4 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.2.2 Generate WBS | Everyone | 0% | 2020-02-04 | 2020-02-10 | 4 | 7 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.2.2.1 determine components of project | Everyone | 0% | 2020-02-04 | 2020-02-07 | 2 | 4 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.2.2.2 determine cost and time to each component | Everyone | 0% | 2020-02-04 | 2020-02-07 | 2 | 4 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.2.2.3 assign member to each component | Everyone | 0% | 2020-02-08 | 2020-02-09 | 1 | 2 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.2.2.4 determine risk factors for each component | Everyone | 0% | 2020-02-10 | 2020-02-11 | 1 | 2 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.2.3 Measure area and assign co-ords | Everyone | 0% | 2020-02-11 | 2020-02-14 | 2 | 4 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.2.4 Research risk's and limitations | Everyone | 0% | 2020-02-11 | 2020-02-15 | 3 | 5 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
1.3 Purchase Items
| 1.3.1 Discuss required materials | Everyone | 0% | 2020-02-13 | 2020-02-22 | 6 | 10 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.3.2 Dollarama spree | Everyone | 0% | 2020-02-19 | 2020-02-28 | 6 | 10 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.3.3 collect materials from home | Everyone | 0% | 2020-02-23 | 2020-03-02 | 5 | 9 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.3.4 report earned value analysis | Everyone | 0% | 2020-03-05 | 2020-03-14 | 6 | 10 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
1.4 Project Scheduling and Planning
| 1.4.1 Gannt Diagram Development | Everyone | 0% | 2020-02-11 | 2020-02-12 | 1 | 2 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.4.2 Network Activity Diagram | Everyone | 0% | 2020-02-13 | 2020-02-14 | 1 | 2 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.4.3 Monitor and Control Planning | Everyone | 0% | 2020-02-11 | 2020-04-07 | 34 | 57 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
1.5 Build RGM
| 1.5.1 Build Team Member 1 section | Everyone | 0% | 2020-03-21 | 2020-03-27 | 21 | 7 | [84 empty] | This task was originally done by Hedeya, since she was removed from the project, the new comprimise was to have everyone work on her task and then we would all branch off and work on our own. (Total Man hours /3)
| 1.5.2 Build Team Member 2 section | Everyone | 0% | 2020-03-21 | 2020-03-27 | 21 | 7 | [84 empty] | This task was originally done by Kajal, since she was removed from the project, the new comprimise was to have everyone work on her task and then we would all branch off and work on our own. (Total Man hours /3)
| 1.5.3 Build Team Member 3 section | Nada | 100% | 2020-03-27 | 2020-04-16 | 21 | 21 | [84 empty] | This task has not changed from the original proposed Gant
| 1.5.4 Build Team Member 4 section | Abigail | 100% | 2020-03-27 | 2020-04-16 | 21 | 21 | [84 empty] | This task has not changed from the original proposed Gant
| 1.5.5 Build Team Member 5 section | Nicholas | 100% | 2020-03-27 | 2020-04-16 | 21 | 21 | [84 empty] | This task has not changed from the original proposed Gant
1.6 RGM Operate and Tear Down
| 1.6.1 RGM Operate | Everyone | 0% | 2020-04-16 | 2020-04-17 | 1 | 2 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.6.2 Tear Down | Everyone | 0% | 2020-04-17 | 2020-04-18 | 1 | 2 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.7 Reflect on the Project | [90 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.7.1 Video Submission | Everyone | 0% | 2020-04-16 | 2020-04-17 | 1 | 2 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.7.2 Determine final earned value analysis | Everyone | 0% | 0 | 1899-12-31 | 1 | 2 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)
| 1.7.3 Final meeting (celebration) | Everyone | 0% | 2020-04-16 | 2020-04-17 | 1 | 2 | [84 empty] | Since this task included everyone, we took the amount of work hours needed from the original task and then we divided it by 3 (amount of current employes)